## Slide 1: Tappa Tappa Keyboard
Julia Abdel-Monem
Jason Culbertson
Ferris Hammes-Buehler
Taran Haug
Gavin Haynes

## Slide 2: Hero Climb
  Our 2D platformer, with different classes and roguelike elements!
Queue the Demo!

## Slide 3: Individual Work

## Slide 4: Ferris
Ferris (TL1) |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Requirements Collection | 2 | 1 | 100% |  |  |  |  |  |  |  |  |  | 
Sprite Design | 4 | 2 | 35% |  |  |  |  |  |  |  |  |  | 
Controller Design | 3 | 3 | 100% |  |  |  |  |  |  |  |  |  | 
Level Creation | 6 | 0 |  |  |  |  |  |  |  |  |  |  | 
Programming | 5 | 3 | 80% |  |  |  |  |  |  |  |  |  | 
Testing | 3 | 1 |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Taran
Taran (TL2) |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Requirements Collection | 4 | 2 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Asset Collection | 3 | 1 | 70% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tileset Construction | 4 | 4 | 80% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rising Lava | 4 | 1 | 50% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level Piece Design | 20 | 3 | 20% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level Procedural Generation | 15 | 2 | 20% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Enemy and Collectible Integration | 5 | 0 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: Gavin
Gantt chart not updated yet
Largely not needed for MVP
Set up a sound for MVP to use.

## Slide 7: Jason
Jason (TL5) |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Research AI patterns for 2d Platformers | 2 | 2 | 100.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design Basic Enemy Behavior | 3 | 2 | 50.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implement Pathfinding Algorithms | 4 | 3 | 50.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create State Machine | 3 | 0 | 0.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Program Enemy Attack Patterns | 3 | 0 | 0.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop Collision Detection for Enemies | 2 | 2 | 100.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 8: Julia
Gantt chart not updated yet
Built interface
Created Main Menu
Created Character Selector

## Slide 9: Cost So Far
 | Total |  | 
 | Budgeted | Actual | Deficit
Ferris | $2,500.00 | $1,000.00 | $1,500.00
Taran | $6,000.00 | $1,500.00 | $4,500.00
Gavin | $1,500.00 | $100.00 | $1,400.00
Jason | $2,500.00 | $800.00 | $1,700.00
Julia | $2,500.00 | $1,000.00 | $1,500.00
Total | $15,000.00 | $4,400.00 | $10,600.00

## Slide 10: Any Questions?
Thank you!